## PGCo
WSSC Water Projects: September 1, 2025 through September 1, 2028 (Prince George's County)
POTENTIAL PROJECT IMPACT
ID | Project Number | Project Name | Project Type | Project Status | Scope of Work | County | Council District | Location | Impacted streets | Start date | Completion Date | On Going (In Construction) | Odor | Noise | Traffic
1 | BT6618A18 | White Oak 20" WMR | WMR - BT | Construction | Replacement of 1.47 miles | MC & PG | 5:1 | Silver Spring (MO) & Beltsville (PG) | Gracefield Road, Cherry Hill Road, Powder Mill Road, Calverton Blvd, Plum Orchard Road, Rumsfield Ter, Major Denton Drive,Swallow Falls Ct, | Quarter 2, 2025 | Quarter 4, 2026 | Yes
2 | BR7653A23 | Kemp Mill Estates WMR | WMR - BR | Design | Replacement of 1.98 miles | MC & PG | 6 | Silver Spring | Bromley Street, Fillmore Drive, Fulham Court, Fulham Street, Holborn Street, Horton Drive, Kemp Mill Road, Kersey Road, Monticello Avenue, N Belgrade Road | Quarter 4, 2027 | Quarter 2, 2029 | No
3 | BT6289A17 | Allentown Rd 42 Inch WMR | WMR - BT | Construction | Replacement of 3.57 miles | PG | 8 | Camp Springs | Allentown Road between Old Branch Avenue and Temple Hill Road | Quarter 1, 2022 | Quarter 2, 2026 | Yes
4 | BR6060A16 | Audrey WMR | WMR - BR | Construction | Replacement of 2.83 miles | PG | 8 | Oxon Hill | Chester Rd.; Hampton Dr.; Kennebec St.; Maury Ave.; Maury Pl.; Roseld Ct.; Audrey Ln.; Deal Dr.; Glassmanor Dr.; Neptune Ave.; Indian Head HGWY.; Irvington St.; Winthrop St.; Owens Rd.; Devitt Pl. | Quarter 1, 2024 | Quarter 2, 2026 | Yes
5 | BR6508A18 | Goucher Dr WMR | WMR - BR | Construction | Replacement of 2.23miles | PG | 3 | Berwyn Heights | Charlton Avenue, Cunningham Drive, Marietta Lane, 58th Avenue, Goucher Drive, Natasha Drive Bucknell, Terrace Villanova Road, Paxton Court, Swarthmore Drive, Berwyn Road ,Nevada Street, Vernon Terrace | Quarter 1, 2025 | Quarter 1, 2026 | Yes
6 | BR6655A19 | CHELTENHAM WMR | WMR - BR | Construction | Replacement of 0.63 miles | PG | 9 | Clinton | Cheltenham Avenue, Edison Drive, Dangerfield Road, Dorian Lane, Dangerfield Place, Echo Lane | Quarter 1, 2025 | Quarter 4, 2025 | Yes
7 | CI6851P20 | Gallahan Road Sewer Rehabilitation Project _ Area 8_CTO 04-07 | Sewer Roads | Design | Rehabilitation, or replacement of 1.75 miles. | PG | 9 | CLINTON | Gallahan Road, CHALFONT AVE, TAYLOR AVE, DAUPHIN CT,TRAFALGAR DR, ROSALIE DR,TINKER DR,TALL TIMBER CT | Quarter 1, 2026 | Quarter 3, 2027 | No | Yes | Yes | Yes
8 | CRCKCILRMH7820A24 | Capitol Heights Roads | Sewer Roads | Design Complete | Rehabilitation, or replacement of 2.24 miles. | PG | 6 | Capitol Heights | Abel Ave, Akin Ave, Altoona St, Balboa Ave, Bayou Ave, Brenner St, Capitol Heights Blvd, Chamber Ave, Clovis Ave, Cumberland St, Dole St, Doppler St, Drum Ave, Emmet St, Faye St, Larchmont Ave, Nova Ave, Central Ave, Opus Ave, and Quire Ave. | Quarter 1, 2026 | Quarter 2, 2027 | No | Yes | Yes | Yes
9 | CRCILRMH7980A25 | Penn Ave Sewer Rehabilitation | Sewer Roads | Design | Rehabilitation, or replacement of 2.3 miles of sewer mains and 75 manholes in the Oxon Run Basin. | PG | 7 | Boulevard Heights | Dupont Ave, Houston St, Fort Dr, Silver Hill Rd, Lewis Ave, Davis Ave, Brooks Dr, Medora Dr, Porter Ave, Lacy Ave, Homer Ave, Huron Ave, Lamar Ave, Lakewood St, Lakewood Ave, Campbell Dr, Urn St, Vine St, Will St, Torque St, Billings Ave, Shell St, Rail St, Quinn St, Nova Ave, Edgewick St, Omaha St | Quarter 1, 2026 | TBD | No | Yes | Yes | Yes
10 | CRCILRMH8041A25 | Lower Anacostia Roads Planned | Sewer Roads | Planning | Rehabilitation, or replacement of 3 miles. | PG |  | TBD | TBD | Quarter 1, 2026 | TBD | No | Yes | Yes | Yes
11 | BR7214B21 | Cheverly Phase II WMR | WMR - BR | Design | Replacement of 2.33 miles | PG | 5 | Cheverly | Cheverly Circle, Crest Avenue, Crestlawn Avenue, Dewey Street, Euclid Street, Forest Road, Greenleaf Road, Hawthorne Street, Lake Avenue, Park Way, and Valley Way | Quarter 1, 2026 | Quarter 2, 2028 | No
12 | BR7214A21 | Cheverly Phase I WMR | WMR - BR | Design | Replacement of 1.51 miles | PG | 5 | Cheverly | 57th Avenue, 57th Place, 59th Avenue, 59th Place, Beecher Street, Belmont Street, Carlyle Street, Crest Avenue, Hospital Drive, Lydell Road, Pepsi Place, Schuster Drive, Valley Way | Quarter 1, 2026 | Quarter 2, 2028 | No
13 | BTBR7062A21 | Furman Pkwy 24" WMR | WMR - BT/BR | Design | Replacement of 0.99 miles | PG | 3 | Riverdale | Furman Pkwy, Greenvale Pkwy, 67th Ave.Emerson Street, Valley Street, Ingraham Street, Beacon Light Road, Patterson Street, | Quarter 1, 2026 | Quarter 3, 2027 | No
14 | CICRLRMH8026A25 | Beaverdam - Glenarden | Sewer Roads | Design Complete | Rehabilitation, or replacement of approximately 2.18 miles of sewer main and 0.36 miles of defective laterals, and seventy - four (79) manholes in Beaverdam Basin, Prince George's County, Maryland. CTO 122 | PG | 5 | Glenarden | 73rd Ave, Parkwood St, Ardwick Ardmore Rd, 91st Ave, Taylor St, Volta St, Wallace Road, Jefferson St, 7th Street, Edwards St, Gary Lane, Mc Lain Ave, E Glenreed Ct, Brightseat Road, Reicher Street, Kelner Dr, Musclewood Ct, Glenarden Pkwy, Wesley St, 5th St,Tyler Ct, Grant Dr, Polk St, Piedmont Ave, 75th Ave, Fairwood Rd, Manson St, 82nd Ave, 74th Ave, 3rd St, Kelner Dr, Wesley St, Manson Pl. | Quarter 1, 2026 | Quarter 4, 2026 | No | Yes | Yes | Yes
15 | CICRLRMH8027A25 | Beaverdam - Dodge Park | Sewer Roads | Design Complete | Rehabilitation, or replacement of approximately 2.12 miles of sewer main and 0.67 miles of defective laterals, and ninety - five (95) manholes in Beaverdam Basin, Prince George's County, Maryland. CTO 123 | PG | 5 | Dodge Park | Ardwick Ardmore Rd, Taylor Street, Wallace Rd, Glenarden Pkwy, Polk St, 75th Ave, , Wesley St, , West St, Annapolis Rd, Varnum St, Whitfield Chapel Rd, Hobart St, Mahnaz Ct, Hamlin St, Leslie Ave, Reed St, Johnson Ave, Sterling St, Tyler St, Church St, Fiske Ave, Hayes St, Echolls Ave, Dellwood Ave, Bealls Pleasure Lane, Mason St, 81st Ave, Evarts St, Cawker Ave | Quarter 1, 2026 | Quarter 4, 2026 | No | Yes | Yes | Yes
16 | BR7667A23 | Water Main Installation and PRV Replacement | WMR - BR and PRV | Design | Replacement of 0.38 miles | PG | 8 | Fort Washington | Riverview Road, St Andrews Dr, Swan Creek Road, Livingston Road, W Tantallon Dr, and Old Fort Rd | Quarter 1, 2028 | Quarter 3, 2028 | No
17 | CI6526B18 | Task Order No. 201 - Job No. CI6526B18 - Beaverdam Branch Basin | Sewer Roads | Construction | Rehabilitation, or replacement of 4.16 miles | PG | 5 | Town of Cheverly | Cheverly Park Dr, Wayne Pl, Park Way, Forest Rd, Inwood St, Laurel Ave, Wayne Pl, 64th Ave, Jason St, 63rd Ave, 63rd Pl, Hillside Ave, Parkway Pl, Cheverly Ave, Parkway Pl | Quarter 2, 2022 | Quarter 4, 2026 | Yes | Yes | Yes | Yes
18 | CI6311B17 | Beaverdam Roads Project - CTO 030 | Sewer Roads | Construction | Rehabilitation, or replacement of 2.02 miles | PG | 3 | Town of Cheverly, Hyattsville, Capitol Heights | Tuxedo Rd, Arbor St, Beecher St, Valley Way, 59th Pl, 59th Ave, Lake Ave, Carlyle St, Dewey St, Euclid St, Creston St, 50th Ave, 51st Ave, Schuster Dr, L Street | Quarter 2, 2023 | Quarter 3, 2025 | Yes | Yes | Yes | Yes
19 | CR7306B22 | Broad Creek Basin - Fort Washington & Temple Hills - CTO 72 | Sewer Roads | Construction | Rehabilitation, or replacement of 2.17 miles | PG | 8 | Fort Washington | DIAS DR, ASBURY RD, EAST SWAN CREEK RD, BEECH ST, OLD CANNON ROAD, THORNTON DR, TOR BRYAN RD, DANIA DR, RHODESIA AVE, GRIFF DR, OLD FORT RD, TUCKER RD, BROAD CREEK DR, WEDGEWOOD PL, RIVERHILL RD, ARAGONA DR, TURNER ST, KERBY HILL RD, ELROY PL, CEDAR RIDGE DR, ABBINGTON DR, DOMINION DR, MURRAY HILL DR, CAREY BRANCH DR, CAREY BRANCH DR, LIVINGSTON RD, CATONE CT, BRODERICK DR | Quarter 2, 2024 | Quarter 3, 2025 | Yes | Yes | Yes | Yes
20 | CI7447B22 | Oxon Run Basin - ESA Sanitary Sewer Rehabilitation - CTO 18-26 | Sewer ESAs | Construction | Rehabilitation, or replacement of 1.85 miles | PG | 7 | Oxon Hill, Fort Washington, Temple Hills, Suitland, Capitol Heights, Forestville, District Heights | LIVINGSTON RD, OXON HILL RD, BUCKLAND CT, KENNEBEC ST, ST BARNABAS RD, CATSKILL ST, ANVIL LN, 23RD PKW, 28TH PKW, GOOD HOPE AVE, OLD SILVER HILL RD, BRANCH AVE, OLD SILVER HILL RD, SUITLAND RD, SHADYSIDE AVE, BROOKS DR, PENNSYLVANIA AVE, OLD SILVER HILL RD, TIBER DR, WALKER MILL RD, MARLBORO PK, SAMUEL DR, ALLENTOWN RD | Quarter 2, 2024 | Quarter 3, 2025 | Yes | Yes | Yes | Yes
21 | CI7467B22 | CI7467B22 - CTO 14-29 - AM-Liner | Sewer ESAs | Construction | Rehabilitation, or replacement of approximately 0.84 miles of sewer main and thirty four (34) manholes in Western Branch Basin, Prince George's County, Maryland. CTO 14-29 | PG | 5 | Lanham | DEREKWOOD LN, ARNOLD DR, PARLIAMENT PL, ANNAPOLIS RD, FOWLER LN, RW FONTANA DR, ANNAPOLIS RD, BUENA VISTA AVE, WORRELL AVE, 93RD PL, CIPRIANO RD, GOOD LUCK RD, FRANKLIN AVE, 97TH AVE, TUCKERMAN CT | Quarter 2, 2024 | Quarter 3, 2025 | Yes | Yes | Yes | Yes
22 | BT6824A19 | S. Osborne Rd 30" WMR | WMR - BT | Construction | Replacement of 3.67 miles | PG | 9 | Upper Marlboro | Brentwood Drive, Carroll Court, Crain Highway (US 301), Rolling Glen Way, S Osborne Road | Quarter 2, 2024 | Quarter 3, 2025 | Yes
23 | CI7311A22 | Western Branch ESA - TO#1 | Sewer ESAs | Construction | Rehabilitation, or replacement of approximately 2.34 miles of sewer main and 0.01 miles of defective laterals, and seventy (17) manholes in Western Branch Basin, Prince George's County, Maryland. CTO 14-10 | PG |  | Forestville/District Height | Walker Mill Rd, Wintergreen Ave, Dumont St, Shady Glen Dr, Starboard Dr, District Height Pkwy, Berry Pl, Kipling Pkwy, Ritchie Rd & Richville Dr | Quarter 2, 2025 | Quarter 2, 2026 |  | Yes | Yes | Yes
24 | BR6473A18 | Edward Dr WMR | WMR - BR | Construction | Replacement of approximately 1.52 miles of 4-inch and 8-inch water mains | PG | 9 | Clinton | Cushwa Drive, Brooke Jane Drive, Edward Drive, Penny Avenue, Kaine Drive, Marlee Avenue, Shirl Court, Brandywine Road, Elysse Drive, Flowering Tree Court, Keystone Avenue, Eilerson Street, Hermitt Street, Fulford Street, Groveton Drive, Danford Drive. | Quarter 2, 2025 | Quarter 1, 2026 | Yes
25 | BR7706A24 | Jervis St WMR | WMR - BR | Construction | Replacement of approximately 1.37 miles of 4-inch, 8-inch, and 10-inch water mains. | PG | 9 | Clinton | Kidder Road, Hillantrae Drive, Minnehan Court, Strawberry Hill Drive, Jervis St, Strawberry Court, Strawberry Hill Place, Jervis Court, and Jervis Place. | Quarter 2, 2025 | Quarter 2, 2026 | Yes
26 | BT7168A21 | Leland Str 60" LVVR | LVV | Construction | Replacement of LVV | PG | 1 | Chevy Chase | Woomont Avenue., Strathmore Street,Wisconsin Ave, Leland Street | Quarter 2, 2025 | Quarter 1, 2026 | Yes
27 | CRCILRMH7860A25 | Sligo Creek Roads to#4 | Sewer Roads | Design | Rehabilitation, or replacement of 2.94 miles. | PG | 2 | Hyattsville | 14th Ave, 14th Pl ,15th Ave, 15th Pl, 16th Ave, 19th Ave, 20th Ave, Asbury Ct, Balfour Ct, Balfour Dr, Burgess Dr, Chillum Rd, Cypress Creek Dr, Jefferson St, Legation Rd, Longford Dr, Longfellow St, Madison St, Nicholson St, Oakdale Dr, Parker Ave, Parkway Ct, Ray Rd, Sargent Rd, Timber Creek Ter, Timber Ridge Ln, Torrey Pl, Twin Oak Dr, Westland Dr, Valley Dr. | Quarter 2, 2026 | Quarter 4, 2027 |  | Yes | Yes | Yes
28 | CKCRCILRMH7873A25 | Sligo Creek Roads to#5 | Sewer Roads | Design | Rehabilitation, or replacement of 3.06 miles. | PG | 2 | Hyattsville | 8th Avenue, 8th Place, 9th Avenue, 10th Place, Belle Court, Berkshire Drive, Chillum Road, Chillumgate Road, Chillum Manor Road, Cox Avenue, Eastern Avenue, Elliot Place, Fairoak Avenue, Fairoak Drive, Flander Drive, Karlson Avenue, Karlson Court, Knollbrook Drive, Medwick Drive, New Hampshire Avenue, Ray Road, Riggs Road, Rittenhouse Street, Rosedale Drive, Rosedale Place, Sheridan Street, Somerset Place, Talbert Lane, and Thurman Avenue | Quarter 2, 2026 | Quarter 4, 2027 |  | Yes | Yes | Yes
29 | TBD | Broadcreek Creek Detailed ESA Planned 1 | Sewer ESAs | Planning | Rehabilitation, or replacement of 2 miles. | PG | 0 | Waggaman Heights | TBD | Quarter 2, 2026 | TBD |  | Yes | Yes | Yes
30 | BR6479A18 | Locris Dr WMR | WMR - BR | Design Complete | The replacement of approximately 17,154 feet of 4-inch, 8-inch, 10-inch and 12-inch water mains, as well as 258 water house connections. | PG | 9 | Upper Marlboro | Nottingham Dr; Nottingham Ct; Shield Ct; Victoria Dr; King Richard Dr; Robing Hood Dr; Thomas Dr; Locris Dr; Locris Ct; Healy Pl; Healy Ct; Gambier Dr; Cone Ct; Varus Pl; Shield Dr; Victoria Pl; Rosemont St; Rosemont Ct; Montrose St; Dublin Pl; Woodyard Rd; Mizar Dr; Arrowhead Dr; Dower House Rd | Quarter 2, 2026 | Quarter 2, 2028 | No
31 | BRCRLR6624A19 | Baltimore Ave WMR | WMR - BR | Design | Replacement of 1.44 miles | PG | 5:2 | Hyattsville | 41st place, 42nd place, 46th Avenue, 44th Avenue Baltimore Avenue (ALT. US.1), Burlington Drive, Charles. L. Armentour Drive, Crittenden street, Decatur Street, Emerson Street, Rhode island Avenue (U.S. 1), Rhode island Avenue (Service Road) | Quarter 2, 2026 | Quarter 4, 2027 | No
32 | BT7372A22 | 42" Large Valve Vault Replacement | LVV | Design | Replacement of LVV | PG | 4 | Greenbelt | Greenbelt Road, Lakecrest Drive and Lakecrest Circle | Quarter 2, 2026 | Quarter 4, 2026 | No
33 | BT7241A21 | PISCATAWAY II 16" WMR | WMR - BT | Design | Replacement of 1.87 miles | PG | 9 | Clinton | Piscataway Road, Delancey Street, Welch Street, King Gallahan Court, Mary Catherine Drive, Mary Catherine Court, Windbrook Drive, Hillantrae Drive and Parker Lane | Quarter 2, 2026 | Quarter 4, 2027 | No
34 | BT7244A21 | 450A High Zone 48" Main & 24" FCV Replacement | WM - BL and FCV | Design | Replacement of 0.34 miles | PG | 6 | Upper Marlboro | I-495 Ramp | Quarter 2, 2026 | Quarter 1, 2027 | No
35 | BT7171AB21 | Woodyard Large Valve Vault | LVV | Design | Replacement of LVV | PG | 9 & 4 | Clinton & Bowie | Woodyard Rd (MD 223) & Penn Manor Lane | Quarter 2, 2026 | Quarter 1, 2027 | No
36 | BR7258A21 | Riverview Road WMR | WMR - BR | Design | Replacement of 2.85 miles | PG | 9 | Fort Washington | Riverview Road, Battlement Lane ,Broad Creek Drive, Gates Drive, West Riverview Road, Colleen Court, Sero Estates Drive, Swan Creek Road, Hatton Point Road | Quarter 2, 2027 | Quarter 3, 2029 | No
37 | BTBR7327A22 | Silver Hill Rd 30" WMR | WMR - BT/BR | Design | Replacement of 1.92 miles | PG | 7 | District Heights | Navy Day Drive, Parkway Terrace, Porter Lane, Randall Road, Silver Hill Road, Suitland Road, and Swann Road | Quarter 2, 2027 | Quarter 4, 2028 | No
38 | BR7650A23 | Glenarden WMR | WMR - BR | Design | Replacement of 2.79 miles | PG | 5 | Glenarden | Glenarden Parkway, Reed Street, Leslie Ave, Wesley Street, Fulton Ave, Mclain Ave, Irvin Ave, 1st Street, 2nd Street, 3rd Street, 4th Street, 8th Street, 9th Street, Reicher Street, Kelner Street, Hamlin Street, Amador Drive | Quarter 2, 2027 | Quarter 1, 2029 | No
39 | BR6545A18 | Horizon Way WMR | WMR - BR | Construction | Replacement of 2.17 miles | PG | 6 | District Heights | Daniel Drive, Berry Lane, Berry Place, Altamont Place, Bethany Drive, Anny Drive, Brewton Street, Brewton Court, Wintergreen Court, Glendora Drive and Glendora Court. | Quarter 3, 2024 | Quarter 2, 2026 | Yes
40 | BR6625A19 | Allentown Rd WMR | WMR - BR | Construction | Replacement of 1.17 miles | PG | 8 | Fort Washington | ALDERTON, ALLENTOWN, CALYDON, LUCILLE, OAKLAWN, DALEWOOD, MARSTON, DUNLOW, ALDERTON, STONESBORO, STEED RD | Quarter 3, 2024 | Quarter 4, 2025 | Yes
41 | BT5273F11 | Clinton Zone 42” Water Main Phase IV | WM - BL | Construction | Replacement of 1.96 miles | PG | 9 | Clinton | Brandywine Road,Surratts Road | Quarter 3, 2024 | Quarter 4, 2026 | Yes
42 | BT6625A19 | Allentown Rd 16" TWMR and FCV | WMR - BT and FCV | Construction | Replacement of 1.09 miles | PG | 8 | Fort Washington | Allentown Rd; Stonesboro Rd; Oaklawn Rd; Steed Rd; Lucille Dr; Marston Dr; Calydon Ct; Alderton Ave; Dunlow Ln; Dalewood Rd | Quarter 3, 2024 | Quarter 2, 2026 | Yes
43 | CK7311B22 | CK7311B22 - CTO 14-10 - SAK | Sewer ESAs | Construction | Rehabilitation, or replacement of approximately 2.34 miles of sewer main and 0.01 miles of defective laterals, and seventy (17) manholes in Western Branch Basin, Prince George's County, Maryland. CTO 14-10 | PG | 7:8 | District Heights | Walker Mill Rd, Wintergreen Ave, Dumont St, Shady Glen Dr, Starboard Dr, District Heights Pkwy, Berry Pl, Kipling Pkwy, Dumont St, Loganwood Ct, Marbury Dr, Glendora Dr, Flag Harbor Dr, Rochell Ave, County Rd, Fallsgrove Ln, Richville Rd, Ritchie Rd | Quarter 3, 2025 | Quarter 3, 2026 | Yes | Yes | Yes | Yes
44 | CRCICKLRMH7178A21 | Hyattsville | Sewer Roads | RTA Construction | Rehabilitation, or replacement of 3.23 miles. | PG | 4:2:3 | Hyattsville, Mount Rainer, Takoma Park | 22nd Avenue, Laguna Road, Adelphi Road, Adelphi Court, Curry Drive, New Riggs Road, Riggs Road, 17th Place, 17th Avenue, Langley Way, 26th Place, Osage Street, Merrimac Drive, Keokee Street, Lewisdale Drive, 23rd Place, 23rd Avenue, Longfellow Street, Banning Place, Sheridan Street, Charleston Place, 16th Place, 18th Avenue, Fordham Street, Gumwood Drive, Rosemary Lane, 25th Avenue, Wells Boulevard, Judson Street, Rosette Lane, 15th Avenue, Kennewick Avenue, New Hampshire Avenue, Varnum St, 32nd St, 29th St, Queens Chapel Rd, 28th St, Ingraham St, Hayden Rd, 36th Ave, 34th St, Kaywood Dr, Buchanan St, Arundel Rd, La Salle Rd, The Mall, Hamilton St, Hamilton Manor Dr, Kimberly Rd, 31st Ave, Jamestown Rd, Ager Rd | Quarter 3, 2025 | Quarter 4, 2026 |  | Yes | Yes | Yes
45 | CI7833A24 | Broadcreek Low Impact ESA | Sewer ESAs | Design | Rehabilitation, or replacement of 2.11 miles. | PG | 8:6:7 | Oxon Hiil, Fort Washighton,Temple Hills, Suitland | Allentown Rd, Auth Pl, Auth Rd, Auth Way, Beech Rd, Beech Pl, Bock Rd, Borden Pl, Botetourt Dr, Brinkley Rd, Browns Ln, Cardwell Dr, Carey Branch Rd, Carlton Ave, Claudine Ln, Cumbria Ct, Deer Pond Ln, Devon Hills Dr, Donnell Dr, Doris Dr, Forest Ave, Fort Foote Rd, Hagan Rd, Hartwell St, Henderson Way, Hill Way, Ivanhoe Rd, Kirtland Ave, Lakehurst Ave, Lark Ln, Livingston Rd, Manchester Dr, Marlboro Pike, Marlo Ln, Mercedes Blvd, Messina Dr, Monticello Ct, N Forest Edge Rd, Pleasant Hill Dr, Ridgecraft Dr, Rosecroft Ct, Rosecroft Village Dr, Saint Barnabas Rd, Shagbark Ct, Shallow Creek Ln, Spring Valley Ct, Suitland Rd, Summerhill Rd, Temple Hill Rd, Thornton Pkwy, Traverse Way, Tucker Rd, Vernon Way, Virginia Ln, Weldon Dr, Whitney Pl and Wolf St. | Quarter 3, 2025 | Quarter 2, 2027 |  | Yes | Yes | Yes
46 | CI7175A21 | CI7175A21 - Piscataway Creek Basin | Sewer Roads | Design | The Work to be performed under this Contract consists of the repair, rehabilitation, or replacement of 2.86 miles of defective sewer mains, 0.87 miles of defective sewer laterals, and sixty-four (64) manholes located in the Piscataway Creek Basin, Prince George's County, Maryland. | PG | 8 | TEMPLE HILLS, CLINTON | Taft Road, Lansing Drive, Karen Anne Drive, Kingston Drive, Alderney Place, Allentown Road, Chesterfield Drive, Sheffield Drive, Wessex Drive, Kirby Road, Berkshire Drive, Cloverleaf Avenue, and Colchester Drive, Lansing Drive, Devon Court, Chesterfield Drive, Berkshire Drive, Mansfield Drive, Avon Court, Windsor Drive, Westchester Court, Coolridge Road, Westminster Court, Buckingham Court, and Allentown Road. | Quarter 3, 2025 | Quarter 3, 2026 |  | Yes | Yes | Yes
47 | CI7118A21 | CI7118A21 - PURP Mini Basin 04018, 04019 (Area 15)* | Sewer Roads | Construction | Rehabilitation, or replacement of 1.66 miles. | PG |  | BRANDYWINE, CLINTON | Brandywine Rd, Morano Dr, Lytton Ave, Malthus St, N Crestwood Ave, Groveton Dr, Eilerson St, Danford Dr, Briarcliff Dr, Colorado St, Crafton Ln, Northgate Pkwy | Quarter 3, 2025 | Quarter 3, 2026 |  | Yes | Yes | Yes
48 | BR6652A18 | Thurston Dr WMR | WMR - BR | Design | Replacement of 1.84 miles | PG | 6 | Kettering | Trafton Drive, Trafton Court, Thurston Drive, Wharton Drive, Joyceton Court, Saxton Court, Exeter Court, Bennington Drive, Belton Street | Quarter 3, 2025 | Quarter 1, 2027 | No
49 | BR6558A18 | Darlene Dr WMR | WMR - BR | Construction | Replacement of 1.63 miles | PG | 9 | Clinton | Terence Drive, Wigan Drive, Wigan Court, Darlene Drive, Dee Lane, Spell Court, Parkview Lane and Upton Place | Quarter 3, 2025 | Quarter 4, 2026 | Yes
50 | BR7710A24 | 41st Avenue WMR | WMR - BR | Design | Replacement of 0.48 miles | PG | 2 | Hyattsville | 41st Avenue, Ingraham Street, Gallatin Street, Farragut Street, Emerson Street, Crittenden Street, and 40th Avenue | Quarter 3, 2025 | Quarter 4, 2025 | No
51 | BT7294A22 | 30" Large Valve Vault Replacement | LVV | Design | Replacement of LVV | PG | 5 | Silver Spring | I495 Road off of Colesville Road | Quarter 3, 2025 | Quarter 3, 2026 | No
52 | BT5737B14 | Hannon Street 24" WMR | WMR - BT | Construction | Replacement of 0.34 miles | PG | 4:2 | Takoma Park | Hannon Street, 15th Ave, 16th Ave, 17th Ave, 18th Ave, Riggs Road | Quarter 3, 2025 | Quarter 3, 2026 | Yes
53 | CRCICKLRMH7969A25 | Beaverdam Roads | Sewer Roads | Design | Rehabilitation, or replacement of approximately 2.29 miles of sewer main and 0.48 miles of defective laterals, and seventy - four (74) manholes in Beaverdam Basin, Prince George's County, Maryland. CTO 127 | PG | 7 | Seat Pleasant | 64Th Ave, Adel St, G St, 65Th Ave, 66Th Ave, Martin L Kng Hwy, 69Th Pl, 70Th St, Drylog St, Fresno St, 71St Ave, 68Th St, Seat Pleasant Dr, Addison Rd, 69Th St, Foote St, Field St, 62Nd St, | Quarter 3, 2026 | Quarter 4, 2027 |  | Yes | Yes | Yes
54 | CICKLRMH8011A25 | Beaverdam Roads - Glenarden | Sewer Roads | Design | Rehabilitation, or replacement of approximately 2.0 miles of sewer main and 0.34 miles of defective laterals, and seventy - nine (79) manholes in Beaverdam Basin, Prince George's County, Maryland. CTO 128 | PG | 5 | Glenarden | Mc Lain Ave, Ardwick Ardmore Rd, Whitetire Rd, Irvin Ave, Wesley St, Hamlin St, Mclain Ave, Reicher St, Edwards St, Johnson Ave, 70Th Ave, 72Nd Ave, 4Th St, Wallace Rd, St Johns Pl, Fulton Ave, Tyrol Dr, Edwards St, 75Th Ave, 5th St & 3Rd St | Quarter 3, 2026 | Quarter 4, 2027 |  | Yes | Yes | Yes
55 | AW7413A22 | Lottsford Rd 24" WM Redundancy | BT | Design | Installation of 0.3 miles | PG | 0 | Bowie | Lottsford Rd | Quarter 3, 2027 | TBD | No
56 | CR6851K20 | CR6851K20 - CTO 04-05 - SAK | Sewer ESAs | Construction | Rehabilitation, or replacement of 1.29 miles | PG | 8 | Fort Washington, Clinton | ST ANDREWS DR, Rexburg Ave, Arrow Park Dr, FORT WASHINGTON RD, Bion Dr, Moyer Ct, FIRTH OF TAE DR, Firth of Lorne Cir, Swan Harbour Dr, Loch Loch Carron Cir, Othman Dr, Hollybank Dr, Swan Creek Rd, Swan Harbour Cir, FRIENDSHIP CT, Branch Ave | Quarter 4, 2023 | Quarter 3, 2025 | Yes | Yes | Yes | Yes
57 | CR7301B22 | CR7301B22 - CTO 11-12 - IPR | Sewer ESAs | Construction | Rehabilitation, or replacement of 4.17 miles | PG | 8 | Fort Washington, Temple Hills | KEPPLER RD, HARVEST RD, HARGROVE RD, OLD TEMPLE HILL RD, CRYSTAL LN, PORTAL AVE, TEMPLE HILL RD, TEMPLE HILLS, LAMBERT DR, GULL RD, WALNUT ST, ROBERTS DR, GIFFORD LN, BEACHCRAFT CT, BRINKLEY RD, FARMER DR, LUJEAN LN., BOTETOURT DR, FARMER DR, JANET LN, CARDWELL DR, GLEN OAK DR, BRINKLEY RD, OLD TEMPLE HILL RD, OLD TEMPLE HILLS RD, HARLEY LN, WELDON DR, HOPE DR, SIMMONS LN, CEDELL PL, WESTRIDGE CT, SUMMERHILL RD, LAKEVIEW DR, SHARON RD, SUMMERHILL RD, RAYBURN DR, TOBY DR, TIPTON DR, MIDDLETON LN, COLONIAL DR, CARRIAGE DR, STRATTON RD, ACORN DR, NORTHAM RD, STRATFORD RD, COLLINSON CT, EDGEMERE DR, DODGE LN, THUMAN DR, REDD LN, BUSHEY DR, SHOPTON DR, JOYCE DR, MARLAIN ST, DELBARTON ST, LORRAINE DR, MARK DR | Quarter 4, 2023 | Quarter 4, 2026 | Yes | Yes | Yes | Yes
58 | CR7305B22 | CR7305B22 - CTO 11-15 - AM-Liner | Sewer ESAs | Construction | Rehabilitation, or replacement of 4.28 miles | PG | 9 | Temple Hills, District Heights, Suitland | Lorraine Drive, Linda Ln, Wilkins Drive, Tyburn Street, Tyburn Ct, Sharon Road, Rayburn Ct, Rayburn Drive, Nile Pl, Dalton Street, Henderson Road, Acton Road, Ludlow Drive, Tolson Road, Edgewood Drive, Kenwood Street, Glenn Hills Roadway, Springwood Drive, Middleton Ln., Acton Road, Brentley Road, Manchester Drive, Ridgecroft Drive, Davis Blvd, Griffith Drive, Morris Avenue, Davis Blvd, Silver Valley Way, Henderson Way, Vernon Way, Oakland Way, Hill Way, Auth Road, Long View Road, Keppler Road, Leisure Drive, St. Barnabas Road, Hartford Hills Drive, Old Branch Avenue, Kingswood Drive, Eaton Drive, St. Barnabas, Mathilda Ln, Randall Road, Keir Drive, Swann Road, Parkway Terrace Dr, Navy Day Dr. | Quarter 4, 2023 | Quarter 3, 2025 | Yes | Yes | Yes | Yes
59 | CI7596B23 | CI7596B23 - CTO 14-24 - SAK | Sewer ESAs | Construction | Rehabilitation, or replacement of approximately 1.21 miles of sewer main and and fourty - seven (47) manholes in Western Branch Basin, Prince George's County, Maryland. CTO 14-24 | PG | 4 | Lanham, Glenn Dale, Greenbelt, Bowie | WORRELL AVE, LANHAM/SEABROOK, 7TH ST, OGDEN PL , CIPRIANO RD, GOOD LUCK RD, TUCKERMAN ST, E FRANKLIN AVE, DUBARRY ST, AEROSPACE RD, GREENSPRING CT, NORDIC , GREENBELT RD, CANNING TER, PHILMONT LN, MANDAN TER | Quarter 4, 2024 | Quarter 4, 2025 | Yes | Yes | Yes | Yes
60 | BR6445A18 | Powhatan WMR | WMR - BR | Construction | Replacement of 1.73 miles | PG | 3 | New Carolton | Oliver St; Kidmore Ln; Powhatan St; Finns Ln; Mentana St; Lamont Dr; Nystrom St; Legation Rd; Topton St; Vicar St; Westbrook Dr | Quarter 4, 2024 | Quarter 4, 2025 | Yes
61 | BR6519A18 | Newburg DR | WMR - BR | Construction | Replacement of 1.56 miles | PG | 3 | Lanham | Heidelburg Court, Heidelburg Road, Kepner Court,Nashville Court, Nashville Road, Newburg Drive and Wilhelm Drive | Quarter 4, 2024 | Quarter 2, 2026 | Yes
62 | BR6706A19 | Karla Road WMR | WMR - BR | Construction | Replacement of 1.47 miles | PG | 8 | Fort Washington | Hart Road, E. Barrett Road, Karla Lane, Murray Hill Drive, Carey Branch Drive, Prentice Court, Barrett Pl., and Alcoa Drive. | Quarter 4, 2024 | Quarter 2, 2026 | Yes
63 | BR6640A19 | Village in the Woods WMR | WMR - BR | Construction | Replacement of 2.71 miles | PG | 5 | Hyattsville | Brightseat Rd, Landover Rd, Sheriff Rd, Ardmore Rd, East St, West St, Glenarden Pkwy, Evarts Rainswood Dr, Barlowe Rd, Ardwick Ardmore Rd, Sterling St, Girard St, Amador Dr, Reicher St, Hamlin St | Quarter 4, 2024 | Quarter 2, 2026 | Yes
64 | CI7707A24 | Forest Heights SMR Roads | Sewer Roads | Design Complete | Rehabilitation, or replacement of 2.73 miles. | PG | 8 | Forest Heights | Black Hawk Dr, Talbert Dr, Cree Dr, Woodland Dr, Fox Way, Iroqiois Way, Mohican Dr, N Huron Dr, Onondaga Dr, Rolph Dr, S Huron Dr, Sachen Dr, Seneca Dr | Quarter 4, 2025 | Quarter 1, 2027 | No | Yes | Yes | Yes
65 | CI7362A22 | Detailed ESA Project TO#14 | Sewer ESAs | Design | 1.33 mile of ESA Sewer main and 36 manholes rehabilitation in the Broad Creek Basin, City of Rosecroft. This includes: pipe and manhole replacement & lining , sewer armoring & restoration. | PG | 7:8 | ROSECROFT | BOCK RD, CALHOUN ST, AND CALVIN ST | Quarter 4, 2025 | Quarter 2, 2026 |  | Yes | Yes | Yes
66 | CI7427A22 | Detailed ESA Oxon Run Ph II | Sewer ESAs | Design | Rehabilitation, or replacement of 2.44 miles of sewer mains and 50 manhole in the Barnaby Run Stream Valley in the Oxon Run basin. | PG | 7 | Hillcrest Heights | Wheeler Road, Wheeler Hill Road, Whispering Willow Court, Birchtree Lane, Iverson Street, Iverson Place, Hidden Pine Lane, and 23rd Parkway. | Quarter 4, 2025 | Quarter 3, 2027 | No | Yes | Yes | Yes
67 | CI7682A24 | Parkway Roads Design | Sewer Roads | Design Complete | Rehabilitation, or replacement of 3.6 miles. | PG | 1 | LAUREL | Main St, School Ln, Montgomery St,Alston Pl, 200 6th St, 200 6th St, 200 6th St, Montgomery St, Lorraine Dr, Washington Blvd, Harrison Dr, Gorman Ave, Reistertown Rd, White Way, Clays Ln, Clays Ln, Whiteway, Sandy Spring Rd, Sandy Spring Rd, Phillip Powers Dr, Nichols Dr, Carroll Ave, Post Office Ave, Alan Dr, Mccahill Rd, 10th St, 4th St, Sandy Spring Rd, Rose Ave Ste 200, 8th St, 5th St, 4th St, 7th St, Gallows Rd, Compton Ave | Quarter 4, 2025 | Quarter 1, 2027 |  | Yes | Yes | Yes
68 | CP7701A24 | Forest Heights Force Main | Sewer ESAs | Design Complete | Rehabilitation, or replacement of 0.51 miles. | PG | 8 | Forest Heights | Huron Dr, Oxon Run Dr, Audrey Ln, Sachem Ln, Indian Head Hwy | Quarter 4, 2025 | Quarter 1, 2027 | Yes | Yes | Yes | Yes
69 | CI7428A22 | Western Branch Roads - TO#22 | Sewer Roads | RTA Construction | Rehabilitation, or replacement of approximately 3.30 miles of sewer main and 0.68 miles of defective laterals, and one hundred and two (102) manholes in Western Branch Basin, Prince George's County, Maryland. CTO 115 | PG | 7 | District Heights | Gateway Blvd, Foster St, Kipling Pkwy, Parkland Dr, Old Silver Hill Rd, Marlboro Pike, Parkland Ct, Viceroy Ave, Sydney Ave, Hansford St, Lansdale St, Senator Ave, Roslyn Ave, Boones Ln, Lakehurst Ave, Kirtland Ave, Mason St, Milford Rd, Judith Ave, Marion St, Maygreen Ave, Newkirk Ave, Orleans Ave, Pumphrey Dr & Martha St | Quarter 4, 2025 | Quarter 2, 2027 |  | Yes | Yes | Yes
70 | CI7583A23 | Beaverdam Low Impact ESA - Inhouse Design | Sewer ESAs | RTA Construction | Rehabilitation, or replacement of approximately 1.1 miles of sewer main and thirteen manoles in Beaverdam Basin, Prince George's County, Maryland. CTO 03-36 | PG | 5 | Hyattsville | Oak Forest Ct, Cheverly Hills Ct, Landover Rd, 63Rd Pl, Forest Rd, Hillside Ave, 64Th Ave, 65Th Ave, Randolph St, Warner Ave, Old Ardwick Ardmore Rd, Decatur Rd, Hanson Oaks Rd, Garden City Dr & Professional Pl | Quarter 4, 2025 | Quarter 2, 2026 |  | Yes | Yes | Yes
71 | CIMH7906A25 | Gorman Ave Low Impact ESA | Sewer ESAs | Design Complete | Rehabilitation, or replacement of 1 miles. | PG | 1 | LAUREL | Harrison Dr, Fairlawn Ave, White Way, Baltimore Ave, Laurel-Bowie Rd, Washington Blvd, Bond Mill Rd, Dome Ave, Montpelier Rd, Contee Rd | Quarter 4, 2025 | Quarter 2, 2026 |  | Yes | Yes | Yes
72 | CI7309A22 | CI7309A22 - Broad Creek Roads Design Task Order 9 | Sewer Roads | Design | Rehabilitation of 4.73 mile of Sewer & 176 manholes in SUITLAND, DISTRICT HTS, FORESTVILLE, FORT WASHINGTON, TEMPLE HILLS, CAMP SPRINGS. This includes: pipe and manhole replacement, lining, lateral replacement & restoration. | PG | 8:9 | fort washington,Suitland, Forstville,Camp Springs,Distract Heights | Armand Ave, Aut Rd, Allentown, Carwell Ave, Morris Ave, Pine Grove,Larkspur Rd, larches Ct, Poplar Rd, Suitland Rd, Morgan Rd, Marianne Dr, Pickett Ct, Marlo Ln, N FOREST EDGE RD FORESTVILLE RD, DONNELL Pl,PINEVALE AVE, PUMPHREY DR, CROSS ST, BELTZ DR, STEWART RD, LEONA ST, DONNELL DR, KIRTLAND AVE,RANDOLPH RD, MAPLE RD, BOXWOOD DR DORIS Dr TESTWAY AVE, TANDOM DR, LARKWOOD AVE, DALEWOOD RD, BRODKIN AVE,CROSSBOW CT,CROSSBOW RD, CAMELOT WAY, LOUGHRAN RD, FORT FOOTE RD | Quarter 4, 2025 | Quarter 1, 2027 |  | Yes | Yes | Yes
73 | CRCILRLLMH7303A22 | CRCILRLLMH7303A22 - Broad Creek TO 8 | Sewer Roads | Design | Rehabilitation of 4.47 mile of Sewer & 147 manholes in SUITLAND, DISTRICT HTS. This includes: pipe and manhole replacement, lining, lateral replacement & restoration. | PG | 7 | Suiland, Distract Heights | SWANN RD,WALNUT AVE,DEMING DR,LEEDS DR, STONECLIFF RD,ROMAIN CT, EASTERN LN,WEST AVE, EAST AVE, RUPERT AVE, SUNSET LN,GREAT OAK DR,KERSHAW ST WALTERS LN, MERRITT ST, VICEROY AVE,SYDNEY AVE, 2913 SYDNEY AVE,PARKLAND DR,WILKINS PL,PARKLAND DR, ADDISON AVE,SKYLINE DR,SKYLINE TERR, ROSE BAY DR, RIDGECREST DR, LUCENTE AVE, FRANK ST, GOODFELLOW DR, DAREL ST, SWALTON AVE, DUBLIN DR,DELTA LN, CABLE AVE,BRAYMER AVE, BARTO AVE, AUTH RD,RIDGECREST DR, RANDOLPH DR | Quarter 4, 2025 | Quarter 4, 2026 |  | Yes | Yes | Yes
74 | CI7337A22 | CI7337A22 - Western Branch Roads (TO 7) | Sewer Roads | Design Complete | Rehabilitation, or replacement of approximately 3.08 miles of sewer main and 0.81 miles of defective laterals, and ninety - four (94) manholes in Western Branch Basin, Prince George's County, Maryland. CTO 114 | PG | 7:8 | District Heights | Marbury Dr, Kipling Pkwy, Kirtland Ave, Ritchie Rd, Foster St, Gateway Blvd, Halleck St, Glendora Dr, Mason St, Lansdale St, Nimitz Dr, Lorring Dr, Oak Glen Way, Helena Pl, Whitney Ave, Ramblewood Dr & Edfeldt Dr | Quarter 4, 2025 | Quarter 1, 2027 |  | Yes | Yes | Yes
75 | CICRCKLLLRMH7247A21 | CICRCKLLLRMH7247A21 - Lower Anacostia Roads Rehab Design | Sewer Roads | Design | Rehabilitation, or replacement of 3.45 miles. | PG | 5:2 | Hyattsville, Bladensburg, Brentwood, North Brentwood | Edmonston Road, Crittenden Street, 41st Avenue, 46th Street, Upshur Street, 48th Street, Baltimore Avenue, Annapolis Road, Webster Street, Taylor Street, 51st Street, Tilden Road, Tilden Street, Varnum Street, 42nd Place, Banner Street, 40th Place, Farragut Street, 40th Street, Rhode Island Avenue, 41st Place, Emerson Street, Banner Street, Webster Street, Rhode Island Avenue, Allison Street, Windom Road, 38th Street, Upshur Street, 39th Street, Cottage Terrace, Bunker Hill Road, Utah Avenue, Volta Avenue, Tilden Street, Wallace Road, 39th Place, Varnum Street | Quarter 4, 2025 | Quarter 2, 2027 |  | Yes | Yes | Yes
76 | CI7298A22 | CI7298A22 - BroadCreek Basin Area 2 (CTO 3) [In Planning} (Broadcreek) -Roads | Sewer Roads | Design | Rehabilitation, or replacement of 4.47 miles. | PG | 7:8 | Fort Washington, Temple Hills | Brinkley Road, Schenley Lane, Cardiff Lane, Larry Avenue, Glen Rock Avenue, Holton Lane, Allentown Road, Hillcroft Place, Border Place, Border Drive, Browns Lane, Rosecroft Boulevard, Haverhill Street, Jerome Drive, Bellefield Avenue, Epping Avenue, Fawley Avenue, Lumar Drive, Marquis Drive, Lenham Drive, Billington Court, Den Meade Avenue, Holiday Avenue, Ravine Drive, Veltri Drive, Temple Hill Road, Spring Terrace, Leslie Avenue, Corkran Lane, Rickey Avenue, Carlton Avenue, Canterbury Way, Keppler Road, Beech Place, Beech Road, Stamp Road, Fisher Road, Barnaby Road | Quarter 4, 2025 | Quarter 1, 2027 |  | Yes | Yes | Yes
77 | CR6995A20 | CR6995A20 - University Park | Sewer Roads | Design | Rehabilitation, or replacement of 2.64 miles. | PG | 0.085417 | University Park, Hyattsville, College Park | Adelphi Road; Baltimore Avenue; Beechwood Road; Claymore Avenue; College Heights Drive; Commander Drive; Hartwick Road; Hunter Street; Pine Way; Rosemary Lane; Sheridan Street; Tuckerman Street; 40th Avenue; 41st Avenue; 43rd Avenue; 44th Avenue; Queens Chapel Road; Underwood Street; Queens Chapel Road; Van Buren Street; Wells Parkway; Woodberry | Quarter 4, 2025 | Quarter 3, 2026 |  | Yes | Yes | Yes
78 | CI7047A21 | CI7047A21 - Oxon Run Hilcrest Hieghts - Phase II | Sewer Roads | Design Complete | Rehabilitation, or replacement of 5.37 miles. | PG | 7 | Hillcrest Heights | Iverson St, Keating St, 22nd Pl, 23rd Pkwy, Saint Clair Dr, 23rd Pl, Lyons St, Beaumont St, Culver St, Raleigh Rd, Riviera St, Norcross St, Saint Clair Pl, Kenton Pl, 27th Ave, Keith St, Essex Ct, Callaway St, Foster Pl, Fairlawn St, 24th Ave, Gaither St, 25th Ave, Dunlap St, Chadwick Terr, Dixon St, Bristol Pl, Berkley St, 25th Pl, Dawson St, Eliot Pl, 26th Ave, Easton St, 28th Pkwy, Buckner Ln, Afton St, Oxon Run Dr, Bellbrook St, Curtis Dr, Everest Dr, 29th Ave, 29th Pl, Colebrook Dr, Gaither St, Fairlawn St, Aberdeen St, Scottish Ave, Andover Pl. | Quarter 4, 2025 | Quarter 1, 2027 | No | Yes | Yes | Yes
79 | BR6634A19 | CABIN BRANCH RD WMR | WMR - BR | Design | Replacement of 2.65 miles | PG | 7 | Capitol Heights | Addison Road S, Central Avenue, Cabin Branch Court, Cabin Branch Road, Clearfield Court, Clearfield Place, Coleton Court, Milfan Drive, Rolling Ridge Drive, St Margarets Drive, and Wilburn Drive. | Quarter 4, 2025 | Quarter 3, 2027 | No
80 | BR6650A19 | Alexandria Dr WMR | WMR - BR | Design | Replacement of 1.70 milles | PG | 8 | Oxon Hill | Alexandria Drive, Riverhill Road, Balmoral Drive E, Balmoral Drive W, Mel Mara Drive, Overlook Court, Alexandria Overlook, Panorama Drive, Vista Terrace | Quarter 4, 2025 | Quarter 2, 2027 | No
81 | BR6709A19 | Pickering Circle WMR | WMR - BR | Design | Replacement of approximately 1.22 miles of 8-inch and 10-inch water mains and 0.4 miles of 4-inch, 6-inch and 8-inch sewer mains. | PG | 6 | Mellwood | Pickering Circle, Windermere Court, Tiverton Place, White House Road, Winsford Avenue, Redditch Court, Woodlawn Boulevard, Duxbury Drive, and Sherrington Court. | Quarter 4, 2025 | Quarter 4, 2026 | No
82 | BR6616A18 | Weldon Drive WMR | WMR - BR | Design | Replacement of 1.2 miles | PG | 6 | Temple Hills | Temple Hill Rd, Weldon Dr, Cedell Pl, Harley Ln, Simmons Ln, Hope Dr, Summerhill Rd, Westridge Ct, Westridge Pl. | Quarter 4, 2025 | Quarter 4, 2026 | No
83 | BR6715A19 | Larkwood WMR | WMR - BR | Design | Replacement of 2.20 miles | PG | 8 | Fort Washington | Larkwood Drive, Pinehurst Drive, Cricklewood Drive, Testway Avenue, Lela Court, Mary Place, Doris Drive, Tandom Drive, Constantine Drive, Chris Court, Bey Court | Quarter 4, 2025 | Quarter 4, 2027 | No
84 | BR5993A16 | Vistula Drive WMR | WMR - BR | Design | Replacement of 1.14 miles | PG |  | Fort Washington | Arden Ln, Gibbons Dr, Lumar Dr, Oakdale St, Oaklawn Rd, Vistula Dr, Waco Dr. | Quarter 4, 2025 | Quarter 4, 2026 | No
85 | BR6944A20 | Rolling Acres WMR | WMR - BR | Design | Replacement of 1.5 miles | PG | 9 | Upper Marlboro & Cheltenham | Dale Dr, Phillips Dr, Carnot Dr, Basel Dr, Farrar Ct, Farrar Ter, Dakin Ct, Angora Ter and Angor Ct. | Quarter 4, 2025 | Quarter 1, 2027 | No
86 | BR7273A22 | Kent Village WMR | WMR - BR | Design | Replacement of 2.92 miles | PG | 5 | Hyattsville | Kent Village Drive, Kent Village Place, East Lombard Street, East Kilmer Street, East Inwood Street, Kent Town Drive, Hawthorne Street, Greeley Road, Greeley Place, Goodland Drive, Markham Lane, Grayridge Lane and Virginia Avenue | Quarter 4, 2025 | Quarter 2, 2028 | No
87 | BT6651A19 | Bock Road 20" TWMR | WMR - BT | Design | Replacement of 2.23 miles | PG | 8 | Fort Washington | Bock Road, Belfast Drive, Browns Lane, Buckland Lane, Hempstead Drive, Holly Drive, Mill Crossing Drive, Kingsway Road, Sourwood Lane and Steuben Avenue | Quarter 4, 2025 | Quarter 4, 2027 | No
88 | BT7141A21 | Annapolis Road TWMR Phae 1 | WMR - BT | Design | Replacement of 1.05 miles | PG | 3 | Lanham & Hyattsville | Annapolis Road (MD 450), from Veterans Parkway (MD 410) to 85th Avenue | Quarter 4, 2025 | Quarter 1, 2027 | No
89 | BT7374A22 | 42" Large Valve Vault Replacement | LVV | Design | Replacement of LVV | PG | 1 | Laurel | Muirkirk Road, Old Baltimore Pike, Cedarhurst Drive, and Brickyard Boulevard | Quarter 4, 2025 | Quarter 1, 2028 | No
90 | BR7259A21 | Fort Washington Road WMR | WMR - BR | Design | Replacement of 2.15 miles | PG | 8 | Fort Washington | Fort Washington Road, Warburton Oaks Drive, Riverview Rd, Kimberly Woods Lane, Kimberly Woods Court, Syria Court, Baron Court, Autumnwood Lane, Flaim Lane, Swan Creek Road, Hickory Drive, Aquarius Court, Gemini Lane and Thaden Avenue | Quarter 4, 2026 | Quarter 4, 2028 | No
91 | BR6704A19 | Dolphin Road WMR | WMR - BR | Design | Replacement of 2.4 miles | PG | 3 | Lanham | Good Luck Rd, Mallery Dr, Woodside Dr, Dolphin Rd, Cipriano Rd, Margo Rd, Kingfisher Ln, Nightingale Dr, Woodside Ct, Chervil Rd, Saffron Dr. | Quarter 4, 2026 | Quarter 4, 2028 | No
92 | BR7026A21 | Buckler Road WMR | WMR - BR | Design | Replacement of approximately 2.2 miles of 4-inch, 8-inch, and 10-inch water mains. | PG | 9 | Clinton | Armor Drive, Paros Drive, Armor Court, Florence Court, Hellen Lee Drive, Turret Lane, Buckler Road, Gredinger Drive, Pin Oak Street, Oak Orchard Court, Pin Oak Court, Oak Leaf Place, and Oak Leaf Court | Quarter 4, 2026 | Quarter 1, 2029 | No
93 | BT7141B21 | Annapolis Road 16" TWMR Phase 2 | WMR - BT/BR | Design | Replacement of 2 miles | PG | 3 | Hyattsville | 62nd Avenue, 64th Avenue, 65th Avenue, 68th Avenue, 68th Place, 69th Avenue, 69th Place, 71st Avenue, 72nd Avenue, Annapolis Road (MD 450), Ardwick Ardmore Road, Chesapeake Road, Cooper Lane, Decatur Street, Gallatin Street, Greenvale Parkway, Surrey Lane, Varnum Street, and Woodlawn Drive | Quarter 4, 2026 | Quarter 2, 2028 | No
94 | BT7285A22 | Danville Road 16" WMR | WMR - BT | Design | Replacement of 2.34 miles | PG | 9 | Brandywine | Danville Road, Lusby Ridge Road, Herbin House Road, Claggett Run Road and S Springfield Road | Quarter 4, 2026 | Quarter 4, 2028 | No
95 | CRLR7335A22 | Mount Oak Road Sanitary Lateral Relocation | Sewer Roads | Design | Rehabilitation, or replacement of approximately 0.03 miles of sewer main and 0.008 miles of defective laterals, and two (2) manholes in Western Branch Basin, Prince George's County, Maryland. | PG | 4 | Mount Oak | Mount Oak Road | TBD | TBD
96 | CKCILRMH7903A25 | Temple Hills ESA Sewer Rehabilitation TO 11-36 BC ESA | Sewer ESAs | Design | 2.31 mile of Sewer rehabilitation in the Broad Creek Basin. This includes: pipe and manhole replacement & lining , sewer armoring & restoration. | PG | 8 | Temple Hills | JOAN LN, JOEL LN, TEMPLE HILLS RD, LESLIE AVE, HENSON DR, KEPPLER PL, HENDERSON RD, KEPPLER RD, RW1 HENSON DR , OLD TEMPLE HILL RD, CRYSTAL LN, TEMPLE HILL RD, RW1 GULL RD, RW2 LAMBERTON DR, RW5 SHARON RD, YORKVILLE RD, RW1 SHARON RD, EDGEWOOD DR, RW KENWOOD ST, OLD BRANCH AVE, RW7 BRADOCK RD, RW4 BEECH RD, RW6 BRADOCK RD, NEWMAN RD | TBD | TBD
97 | BR7523A23 | Joseph Dr WMR | WMR - BT/BR | Construction | Replacement of approximately 0.24 miles of 8-inch, and 10-inch water mains. | PG | 9 | Clinton | Joseph Drive, Katie Street, Marcia Place and Glyns Road. | TBD | TBD
98 | BL5628A13 | 450A PG High Zone 48" TRM | WMR - BT/BR | Design | Installation of 3.93 mile redundancy main in PG County | PG | 6 & 9 | Camp Springs, Morningside, Upper Marlboro | Penn Randall Pl, Burton Ln, Allentown Rd | TBD | TBD
99 | BR7941A25 | Magnolia Terrace WMR | WMR - BT/BR | Design |  | PG | 3 | Lanham | Magnolia Ter | TBD | TBD
100 | BR6609A18 | Breezewood Drive WMR | WMR - BT/BR | Design | Replacement of approximately 1.01 miles of 8" water mains. | PG | 4 | Greenbelt | Breezewood Dr, Cherrywood Ln, Greenbelt Rd | TBD | TBD
101 | BR7651A23 | Hillcrest Heights Water Main Replacement | WMR - BT/BR | Design | The replacement of approximately 9,717 feet of 4-inch, 8-inch, and 12-inch water mains, as well as water house connections. | PG | 7 | Hillcrest Heights | Iverson Street, Gaither Street, Colebrooke Drive, Oakwood Street, 19th Avenue, 20th Pathway, 21st Avenue, 21st Place, 22nd Avenue, and 23rd Avenue | TBD | TBD
102 | BR7647A23 | Carmody Hills WMR | WMR - BT/BR | Design | The replacement of approximately 11,370 feet of 6-inch, 8-inch, and 12-inch water mains, as well as water house connections. | PG | 7 | Capitol Heights | Seat Pleasant Dr.; Cerdar Leaf Ave.; Cutlog St.; Valley Park Rd.; Dateleaf Ave.;Blacklog St.; Joplin St.; Drylog St.; Fernleaf Ave.; Hedgeleaf Ave.; Ivyleaf Ave.; Esslog St. Elmleaf Ave.; Carmody Hills Dr.; Jadeleaf Ave.; Goldleaf Ave.; Clinglog St.. | TBD | TBD
103 | BR7648A23 | District Heights WMR | WMR - BT/BR | Design | Replacement of approximately 2.3 miles of 8-inch, and 4-inch water mains. | PG | 9 | District Heights | Halleck Street, Helena Place, Kipling Parkway, Kirtland Avenue, Landsdale Street, Lorring Drive, Milvale Avenue, Nimitz Drive, Overdale Place, Romona Drive, Roslyn Avenue, Senator Avenue, Whitney Avenue, and Wintergreen Avenue. | TBD | TBD
104 | BR8014A25 | Wedgewood Drive WMR | WMR - BR | Design | Replacement of approximately 2.1 miles of 3-12-inch water mains | PG | 8 | Fort Washington | Fort Foote Rd, Round Table Dr, Wedgewood Dr, Wedgewood Pl, Windermere Turn, Kisconko Turn, Wensel Ln, Pamir Ct, Binyon St, Tribonian Dr | TBD | TBD
105 | CRCICNCNCKLRMH8133A25 | Bladensburg Sewer Rehabilitation Project | Sewer Roads | Design | Rehabilitation and replacement of approximately 2.92 miles of sewer main, including laterals & manholes within the Lower Anacostia Basin. | PG | 5 | Bladensburg & Hyattsville | 53RD PL, 54TH PL, 54TH AVE, 55TH AVE, 55TH PL, 56TH AVE, 56TH PL, 57TH AVE, 58TH AVE, BUCHANAN ST, CHESAPEAKE RD, CRITTENDEN ST, DECATUR ST, DONOVAN PL, EDMONSTON RD, ELBERTON PL, ELBERTON CT, EMERSON ST, FARRAGUT ST, GALLATIN ST, QUINCY ST, SHEPHERD ST, SPRING RD, TAUSSIG RD, TAYLOR ST, TILDEN RD, VARNUM ST | TBD | TBD
106 | CICRLRMH8102A25 | Western Branch Basin Sewer Rehabilitation (DTO#5) | Sewer Roads | Planning | 3.00 mile of Sewer rehabilitation in the Western Branch Basin. This includes: pipe and manhole replacement & lining , sewer armoring & restoration. | PG | 4 & 5 | South Bowie | TBD | TBD | TBD | NO | YES | YES | YES
107 | CICRCKLRMH8103A25 | Beaverdam Basin Sewer Rehabilitation (DTO#6) | Sewer Roads | Planning | 3.40 mile of Sewer rehabilitation in the Beaverdam Basin. This includes: pipe and manhole replacement & lining , sewer armoring & restoration. | PG | 5 & 7 | Peppermill Village & Walker Mill | TBD | TBD | TBD | NO | YES | YES | YES